## Sheet1
Category/name | status | Prority | Dependencies | context/detail | it person
Planing |  |  |  | Orange = done
Concept | done | 1st |  | pyhsics+hotlineMiami
Research:
Hotline Miami |  |  |  | the gamefeel and level design as exapmles | Sujai
Binding of Isaac |  |  |  | want to see how they hadle item pickups/upgrades | Sujai
Hades |  |  |  | origin of trashy 'god' gifts/boss inpiration | Sujai
Real life room research |  |  |  |  | Sujai
Prototype/Verticle:
Attacks | playable | 1st |  | hitboxes & gamefeel | Charlie
Movement/Aim | rebind | 1st |  | want hotline style controls | Charlie
AI | playable | 1st |  | could use variety & polish (not necessary though) | Charlie
Playarea |  | 1st |  | being blocked-out + deciding on player speed | Sam & Chaz
Level blockout | in-progress | 1st |  | tutorial | Sam
Mechanics:
Attack | playable | 1st |  | done in prototype | Charlie
Movement | rebind | 1st |  | done in prototype | Charlie
AI | playable | 1st |  | done in prototype | Charlie
Ragdoll/pyhsics |  | 2nd |  |  | Charlie
knockback |  | 3rd
Equipment |  | 5th
Item-prototype |  | 5th
Levels:
Tutorial |  | 1st |  |  | Sam
Level 1 |  | 2nd |  |  | Sam
Polish:
test materials |  |  |  | test & find materials for use | Sujai
textures/materials
sound
game-feel
variety
Testing
balance (zany) |  |  |  | Iterate based on feedback
Level refinement