## Sheet1
Category/name | status | Prority | Dependencies | context/detail | Assigned
Planing: |  |  |  | Orange = done
Concept | done | 1st |  | pyhsics+hotlineMiami | everyone
Prototype/Verticle:
Attacks | playable | 1st | AI | hitboxes & gamefeel | Charlie
Movement/Aim | playable | 1st | Concept | want hotline style controls | Charlie
AI | done | 1st | Concept | could use variety & polish (not necessary though) needs better detection range | Charlie
Playarea | in-process | 1st | Prototype & level blockout | blocked-out + decided on player speed | Sam & Chaz
Level blockout | done | 1st |  |  | Sam
Mechanics:
Attack | playable | 1st |  | done in prototype | Charlie
Movement | playable | 1st |  | done in prototype | Charlie
AI | playable | 1st |  | done in prototype | Charlie
Ragdoll/pyhsics | playable | 2nd | Attack |  | Charlie
knockback | playable | 3rd | Attack | could be improved but is fine | Charlie
Attack Hitboxes | Started | 2nd | Attack |  | Charlie
Equipment |  | 5th
Item-prototype |  | 5th |  |  | Charlie
Polish:
download sounds |  |  |  |  | Sujai
implement sound |  |  | Prototype
game-feel |  |  |  | player feedback: impacts, camera shake - do through sounds & vfx | Charlie
Testing |  |  |  |  | everyone