## Sheet1
assigned |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Stage | Pre-production | bar: Week 5
Everyone | Concept | Week 1: done; Week 2: Improved
Everyone | Assign Roles/tasks | Week 1: delayed; Week 3: done
Sujai | Hotline Miami Research | Week 1: Start; Week 2: done; Week 3: Improved
Sujai | Binding of Isaac Research | Week 1: Start; Week 2: in-process; Week 3: done
Sujai | Hades Research | Week 2: done
Sujai | Real life room research | Week 2: Start; Week 4: done
Sam | Level Diagrams | Week 2: Start; Week 3: done
Stage | Prototyping | bar: Week 5
Charlie | Ragdoll/physics | Week 2: Start; Week 4: done
Charlie | Attack prototype | Week 2: Start; Week 3: done
Charlie | Movement/Aim prototype | Week 3: Start; Week 4: done
Charlie | AI | Week 2: Start; Week 3: done
Charlie | Beta-ready Attack | Week 4: Start; Week 6: done; Week 7: Improved
Sam & Chaz | Play/test area | Week 4: done
Sam | blockout | Week 3: Start; Week 4: done
Sam & Chaz | Player Speed | Week 4: done
Sam | Populate blockout | Week 4: Start
Charlie | knockback | Week 4: done
Sujai | download textures/materials | Week 3: Start; Week 5: goal
Sujai | test materials | Week 3: Start; Week 4: Start; Week 5: goal
Sujai | download sounds | Week 4: Start; Week 5: goal
Everyone | Playtest | Week 4: Start; Week 5: goal
Everyone | Practise Pitch | Week 5: Start
Luke | Record Gameplay | Week 5: delayed; Week 6: delayed
Luke | Pitch slides ready | Week 3: Start; Week 4: Start; Week 5: goal
Stage | Polish: | Week 7: Start; Week 8: may delay
Charlie | game-feel | Week 7: Start
Visuals
Luke | UI
Everyone | Playtest | Week 7: Start; Week 8: goal
Everyone | Test/Iterate | Week 7: Start; Week 8: goal
Luke | Record Gameplay | Week 8: goal
Stage | Extra (skippable) | Week 7: ahead of schedule; Week 11: Start
Charlie | Item-prototype | Week 7: ahead of schedule
Equipment
extra variety
Luke | Record Gameplay
Stage | Release | Week 11: Start
| pre-Package | Week 11: Start; Week 12: goal
| Record Gameplay | Week 11: Start; Week 12: goal
| improved re-Package | Week 11: Start; Week 12: goal
| Record Gameplay | Week 11: Start; Week 12: goal
| Distribute Digitally | Week 12: goal
| Submit | Week 12: goal