## Sheet1
Category/name | status | Prority | Dependencies | context/detail | Assigned
Planing: |  |  |  | Orange = done
Concept | done | 1st |  | pyhsics+hotlineMiami | everyone
Research: |  |  | Concept
Hotline Miami |  |  | Concept | the gamefeel and level design as exapmles | Sujai
Binding of Isaac |  |  | Concept | want to see how they hadle item pickups/upgrades | Sujai
Hades |  |  | Concept | origin of trashy 'god' gifts/boss inpiration | Sujai
Real life room research |  |  | Concept |  | Sujai
Level Sketchs | done | 1st |  |  | Sam
Prototype/Verticle:
Attacks | playable | 1st | AI | hitboxes & gamefeel | Charlie
Movement/Aim | playable | 1st | Concept | want hotline style controls | Charlie
AI | done | 1st | Concept | could use variety & polish (not necessary though) | Charlie
Playarea | in-process | 1st | Prototype & level blockout | blocked-out + decided on player speed | Sam & Chaz
Level blockout | done | 1st |  |  | Sam
Mechanics:
Attack | playable | 1st |  | done in prototype | Charlie
Movement | rebind | 1st |  | done in prototype | Charlie
AI | playable | 1st |  | done in prototype | Charlie
Ragdoll/pyhsics |  | 2nd | Attack |  | Charlie
knockback |  | 3rd | Attack
Equipment |  | 5th
Item-prototype |  | 5th
Levels:
Tutorial Blockout |  | 1st | Level Sketchs |  | Sam
Level 1 Blockout | done | 2nd | Level Sketchs |  | Sam
Populate Level |  | 3rd | Level blockout | add content to blockouts
Polish:
test materials |  |  |  | test & find materials for use | Sujai
download textures/materials |  |  |  |  | Sujai
download sounds |  |  |  |  | Sujai
apply textures/materials |  |  | Prototype
implement sound |  |  | Prototype
game-feel
variety
Testing
balance (zany) |  |  |  | Iterate based on feedback
Level refinement