## Sheet1
assigned |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Stage | Pre-production | bar: Week 5
Everyone | Concept | Week 1: done; Week 2: Improved
Everyone | Assign Roles/tasks | Week 1: delayed; Week 3: done
Sujai | Hotline Miami Research | Week 1: Start; Week 2: done; Week 3: Improved
Sujai | Binding of Isaac Research | Week 1: Start; Week 2: in-process; Week 3: done
Sujai | Hades Research | Week 2: done
Sujai | Real life room research | Week 2: Start; Week 4: done
Sam | Level Diagrams | Week 2: Start; Week 3: done
Stage | Prototyping | bar: Week 5
Charlie | Ragdoll/pyhsics | Week 2: Start; Week 4: done
Charlie | Attack prototype | Week 2: Start; Week 3: done
Charlie | Movement/Aim prototype | Week 3: Start; Week 4: done
Charlie | AI | Week 2: Start; Week 3: done
Charlie | Beta-ready Attack | Week 4: Start
Sam & Chaz | Playarea
Sam | blockout | Week 3: Start; Week 4: done
Sam & Chaz | Player Speed | Week 4: done
Sam | Populate blockout | Week 4: Start
Charlie | knockback | Week 4: done
Sujai | download textures | Week 3: Start
Sujai | download textures/materials | Week 3: Start
Sujai | test materials | Week 3: Start; Week 4: Start
Sujai | download sounds | Week 4: Start
Everyone | Playtest | Week 4: Start
Luke | Record Gameplay
Stage | Polish:
game-feel
variety
Visuals
UI
Test
iterate
Luke | Record Gameplay
Stage | Extra (skipable)
Equipment
Item-prototype
Luke | Record Gameplay
Stage | Release
Pakage
Record Gameplay
Distribute Digitally